## Ajith
Date | Reports
2025-01-13 | Getting data from APIs, cleaning it, and storing it as a CSV file using pandas.
2025-01-14 | Pongal Holiday
2025-01-15 | Leave
2025-01-16 | Leave
2025-01-17 | planned to practice and work on data cleaning and preprocessing.

## Sandeep
Date | Reports
2025-01-13 | Task: in Findit after uploading to azure_blob deleting the ppts from azure_folder and Azure_updated_ppt_folder.Learning about series and its methods in pandas
2025-01-14 | Holiday
2025-01-15 | Leave
2025-01-16 | Leave
2025-01-17 | completed Learning about series and its methods in pandas.Learning about Dataframes and its methods in pandas

## Manoj
Date | Reports
2025-01-13 | Leave
2025-01-14 | Holiday
2025-01-15 | Improved Forms : Built dynamic forms with real-time validation to enhance user input and data accuracy.
2025-01-16 | UI, Performance, and Reporting Enhancements: Updated the UI for responsiveness, optimized app performance, and enabled PDF report generation with interactive charts.
2025-01-17 | Chatbot, State Management, and Reusable Components: Added a manager chatbot, used React Context for global state, and refactored UI components for reusability.

## Suresh
Date | Reports
2025-01-13 | Leave
2025-01-14 | Holiday
2025-01-15 | Leave
2025-01-16 | Leave
2025-01-17 | Leave

## Basil
Date | Reports
2025-01-13 | Leave
2025-01-14 | Pongal Holiday
2025-01-15 | New Chatbot Approach Development: Developed a new approach for the chatbot by using the SQLTool from LangChain. Fine-tuned the template and improved the inclusion of examples.
2025-01-16 | Chatbot Testing and Template Optimization : Tested the chatbot with different queries, optimized the template, and added additional rules for the template, such as SQL-specific restrictions (e.g., avoiding DELETE statements)
2025-01-17 | Custom Function Creation for SQL Query Generation: Created a custom function, decide_column, which processes the entire table structure text and passes it to the LLM along with a template to identify the correct column and generate the corresponding SQL query

## Dhanesh
Date | Reports
2025-01-13 | Enhanced data validation and cleaning by working with datasets to identify and correct inconsistencies.
2025-01-14 | Pongal Holiday
2025-01-15 | Worked in standardization and normalization techniques for preparing data for analysis.
2025-01-16 | Improved understanding of data de-duplication and its impact on data quality and processing efficiency.
2025-01-17 | Explored on handling missing data, learning to remove incomplete records to maintain dataset integrity.

## Devanathan
Date | Task Carried Out
2025-01-13 | Leave
2025-01-14 | Pongal Holiday
2025-01-15 | working on a tool to analyze CSV defects, generate a TXT report, clean the data based on the analysis, create a cleaned CSV file, and store the cleaned data in a database.
2025-01-16 | Task:Create Flask app that reads a CSV with pandas, calculate stats like count, unique, mean, min, max etc,shows them on a web page.
2025-01-17 | Exploring python library - pyarrow and pyspark